## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Atharva Vilas Jadhav
PROJECT NAME: | Career Path Prediction System
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-08-26
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Prediction System |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Cloud Counselage
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
| 2025-08-23 | The initial machine learning model showed 100% training accuracy but extremely low testing accuracy, indicating severe overfitting. | Technical Challenge | Yes | Always evaluate a model on a separate test set. If overfitting occurs, simplify the model or use regularization techniques. | Replaced the overly complex XGBoost model with a more stable RandomForestClassifier and implemented a feature selection strategy. | Atharva Jadhav | Solved | This iterative process of identifying overfitting and correcting it is a core part of the machine learning workflow.
| 2025-08-24 | The Streamlit application was giving errors because the clean user interface options (e.g., "Self-help" for books) did not match the messy, raw data the model was trained on. | Data Quality | Yes | Implement a robust data cleaning and preprocessing pipeline that is applied consistently to both the training data and any new input data. | Re-engineered the data pipeline to clean and standardize all categorical features before training the model, ensuring a perfect match with the UI inputs. | Atharva Jadhav | Solved | This highlights the importance of "Data First" thinking in machine learning projects.
| 2025-08-25 | The initial user interface used sliders for categorical choices (like "Interested subjects"), which was confusing and illogical for the user. | User Interface/User Experience (UI/UX) | Yes | Always choose UI elements that match the type of data being requested (e.g., dropdowns for choices, radio buttons for ratings). | The UI was redesigned to use dropdown menus for categorical selections and radio buttons for numerical ratings, creating a much better user experience. | Atharva Jadhav | Solved | Good UI/UX is critical for the adoption and success of any application, even a technical one.