## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Career Path Prediction System |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: |  |  | Last Updated date: | 2025-08-27 | Project Team Lead: | Atharva Jadhav |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 8 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | The initial machine learning model might severely overfit the training data. | The model would perform poorly on new, unseen data, making the predictions unreliable and the application useless. | Implement a robust feature selection strategy to train the model only on the most important data, and choose a model less prone to overfitting like RandomForest. | Atharva Jadhav | Critical | 5 | CLosed | Risk
2 | Risk | The quality of the provided dataset is low, with messy and inconsistent categorical data. | If not cleaned properly, the model will learn incorrect patterns, leading to inaccurate predictions. | Develop a comprehensive data cleaning pipeline to standardize all categorical features before training the model. | Atharva Jadhav | High | 3 | Closed | Assumption
3 | Assumption | The user's self-reported skill levels and interests are a reasonably accurate reflection of their true abilities. | If users input inaccurate data, the model's predictions, while technically correct, will not be relevant to the user's actual profile. | The UI is designed to be clear and simple to minimize user error. No further mitigation is possible as it relies on user honesty. | Atharva Jadhav | Moderate | 2 | Closed | Issue
4 | Assumption | The provided PS2_Dataset.csv is representative of the broader student population. | If the dataset is biased (e.g., only contains data from one type of university), the model may not perform well for all users. | This is an accepted assumption for the scope of this proof-of-concept project. | Atharva Jadhav | Low | 1 | Closed | Dependency
5 | Issue | The initial UI design used sliders for categorical choices, which was confusing for users. | Poor user experience could lead to user frustration, incorrect inputs, and a lack of trust in the application's results. | Redesigned the UI to use intuitive components: dropdowns for categorical choices and radio buttons for numerical ratings. | Atharva Jadhav | High | 3 | Closed
6 | Issue | The application was initially slow to load due to a complex hyperparameter tuning process running every time. | A long loading time would make the application impractical for real-time use and lead to a poor user experience. | The hyperparameter tuning process was simplified to run much faster, and Streamlit's caching was used to ensure the model only trains once per session. | Atharva Jadhav | Moderate | 2 | Closed | Open
7 | Dependency | The project requires specific open-source Python libraries to be installed (Streamlit, Pandas, Scikit-learn). | The application cannot be developed or run without the correct software environment and dependencies. | All required libraries were documented and installed in a dedicated virtual environment to ensure reproducibility. | Atharva Jadhav | High | 3 | Closed | Closed
8 | Dependency | The application's functionality relies on the PS2_Dataset.csv file being available. | The model cannot be trained, and the application cannot run if the source data file is missing or corrupted. | The code includes error handling to gracefully manage a missing file and inform the user. | Atharva Jadhav | Critical | 5 | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24